## Tabelle1
Timetable

Day	Hours
28.10	1,5	Setting up repository, time table, readme file and plan app
30.10	5,5	Walking skeleton, router
31.10	2,5	Notifications and redux
31.10	2	Links, bugfixing, upload function
09.11	7,5	Basic upload function, directory, file retrieval
10.11	3,5	Styling, refactoring, bugfixing
15.11	5	download function
16.11	5	File selection, multiple and single file upload, file organisation
17.11	2	Encryption/Decryption
19.11	3	backend tests
20.11	2	bugfixing backend tests + new tests
21.11	3	trying encryption/decryption again -.-
22.11	3	trying encryption/decryption again -.-
24.11	3	trying encryption/decryption again -.-
01.12	8	working encryption and decryption
03.12	4	debugging, refactoring, improved file name creation
11.12	4	profile and admin console
12.12	2	debugging
20.12	5	bruteforce prevention, email verification (buggy)
22.12	5	simple role management, logging
06.01	6	admin can modify every user, extended logging, tried to fix email verification
07.01	5	improved exception handling, started with ordering-renaming uploaded files
08.01	6	ordering, naming, filtering and storing of files
09.01	5	improved name creation for multiple uploaded files, implemented helmet, bugfixing, refactored FilesView
10.01	3	prepared file view when bigger amounts of files are to display, bugfixes, started with a „last used files“ view
11.01	6	'last used view‘ (still buggy), fixed login error message about unmounted components, implemented toJSON() Method, small bugfixes and workarounds, working on a style
12.01	4	deployed to heroku (problems with fs), implemented favourite files view
13.01	3	backend tests
19.01	6	improved design, css, create public download link with one-time-only use and valid till midnight, fixed email verification with mailtrap
20.01	3	Send download link per mail, debugged admin console, improved registration form, introduced parameter file
26.01	6	Refactor exceptions, ui design, responsive
27.01	4	add and delete mime types, delete user,

Currently:	133,5
Needed:	175
Left:	41,5