## Timetable
Timetable

Day	Hours
28.10	1,5	Setting up repository, time table, readme file and plan app
30.10	5,5	Walking skeleton, router
31.10	2,5	Notifications and redux
31.10	2	Links, bugfixing, upload function
09.11	7,5	Basic upload function, directory, file retrieval
10.11	3,5	Styling, refactoring, bugfixing
15.11	5	download function
16.11	5	File selection, multiple and single file upload, file organisation
17.11	2	Encryption/Decryption
19.11	3	backend tests
20.11	2	bugfixing backend tests + new tests
21.11	3	trying encryption/decryption again -.-
22.11	3	trying encryption/decryption again -.-
24.11	3	trying encryption/decryption again -.-
01.12	8	working encryption and decryption
03.12	4	debugging, refactoring, improved file name creation
11.12	4	profile and admin console
12.12	2	debugging
20.12	3	bruteforce prevention
	2	email verification (buggy)
22.12	5	simple role management, logging
06.01	3	admin can modify every user
	3	extended logging, tried to fix email verification
07.01	5	improved exception handling, started with ordering-renaming uploaded files
08.01	6	ordering, naming, filtering and storing of files
09.01	5	improved name creation for multiple uploaded files, implemented helmet, bugfixing, refactored FilesView
10.01	3	prepared file view when bigger amounts of files are to display, bugfixes, started with a „last used files“ view
11.01	3	'last used view‘ (still buggy), fixed login error message about unmounted components
	3	implemented toJSON() Method, small bugfixes and workarounds, working on a style
12.01	4	deployed to heroku (problems with fs), implemented favourite files view
13.01	3	backend tests
19.01	6	improved design, css, create public download link with one-time-only use and valid till midnight, fixed email verification with mailtrap
20.01	3	Send download link per mail, debugged admin console, improved registration form, introduced parameter file
26.01	6	Refactor exceptions, ui design, responsive
27.01	6	add and delete mime types, delete user, add notes
29.01	1,5	delete notes, music category, display notes
30.01	3	added confirmation windows, when user get deleted also his files and notes, bugfixing, filter
31.01	5	add view to add encryption and prepared backend for it, decrypt view, debugging
01.02	2	decryption view including mailing and public link
	2	tried to fix table height problem with different screensizes
02.02	2	toggle file encrypted and decrypted, ensure that admin always exists
	2	adjusted removal of files for unencrypted or encrypted files, adjusted namecreation on backend site, general bugfixing
	1	made my own notification and error event in order to fix a bug
	2	e2e testing
03.02	5,5	e2e testing
04.02	1	e2e testing
	1	add comments
05.02	1	frontend view
	1,5	deployment
	2	making single page application links accessible

Currently:	168
Needed:	175
Left:	7

## Tasks
Open Tasks:

## Bugs
Known Bugs

Sometimes random connection timeout with the backend
Depending on the screen size and container size...the container moves out of the picture
When you remove multiple files, not all disappear immediately from the view