## Tabelle1
Timetable

Day	Hours
28.10	1,5	Setting up repository, time table, readme file and plan app
30.10	5,5	Walking skeleton, router
31.10	2,5	Notifications and redux
31.10	2	Links, bugfixing, upload function
09.11	7,5	Basic upload function, directory, file retrieval
10.11	3,5	Styling, refactoring, bugfixing
15.11	5	Download function
16.11	5	File selection, multiple and single file upload, file organisation
17.11	2	Encryption/Decryption
19.11	3	backend tests
20.11	2	bugfixing backend tests + new tests
21.11	3	trying encryption/decryption again -.-
22.11	3	trying encryption/decryption again -.-
24.11	3	trying encryption/decryption again -.-
01.12	8	working encryption and decryption
03.12	4	debugging, refactoring, improved file name creation
11.12	4	profile and admin console
12.12	2	debugging
20.12	5	bruteforce prevention, email verification

Currently:	71,5
Needed:	180
Left:	108,5